## Project Plan
Task Name | Duration | Start | Finish
Research Phase
Interview Subject Matter Experts | 2 days | 2021-01-01 | 2021-01-04
Search the Web | 2 days | 2021-01-05 | 2021-01-06
Outline Phase
Create outline | 2 days | 2021-01-07 | 2021-01-08
Present to publisher | 1 day | 2021-01-11 | 2021-01-11
Revise Outline | 2 days | 2021-01-12 | 2021-01-13
Review with Subject Matter Expert | 2 days | 2021-01-14 | 2021-01-15
Outline complete | 0 days | 2021-01-15 | 2021-01-15
Development Phase
Write content | 2 wks | 2021-01-18 | 2021-01-29
Add graphics | 1 wk | 2021-02-01 | 2021-02-05
Development complete | 0 days | 2021-02-05 | 2021-02-05
Edit Phase
Check grammar, spelling, and proofread | 2 days | 2021-02-08 | 2021-02-09
Check for technical accuracy | 2 days | 2021-02-10 | 2021-02-11
Review Phase
Approve editing changes | 1 day | 2021-02-12 | 2021-02-12
Meet with editor | 1 day | 2021-02-15 | 2021-02-15
Print Phase | 3 days | 2021-02-16 | 2021-02-18
Print proof | 1 day | 2021-02-16 | 2021-02-16
Review proof | 1 day | 2021-02-17 | 2021-02-17
Print final | 1 day | 2021-02-18 | 2021-02-18
Report Complete | 0 days | 2021-02-18 | 2021-02-18

## Costs
Printing Costs
Ink | 250
Paper | 500
Printer Time | 380
Total | 1130